## Project Plan
Photo Editing
[6 empty] | August |  |  |  | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
Requirement # | Requirement | Task # | Task | Estimate | Owner | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06
2.1 | Smooth Image Dragging | 2.1.1 | Create a function or modify existing function to ensure smooth and responsive image dragging operations, with minimal latency and lag. | 5 Days | Saad
|  | 2.1.2 | Create a function or modify existing to optimize memory usage and prevent excessive resource consumption. | 5 Days | Rohit
|  | 2.1.3 | Testing and buffer | 1 Day | Rohit
2.2 | Error-Free User Interface | 2.2.1 | Gather error reports from internal testing and prioritize critical UI bugs | 3 Days | Saad
|  | 2.2.2 | Fix critical user interface (UI) bugs affecting functionality. | 5 Days | Saad
|  |  | Optimize website performance by addressing slow-loading pages or resources. | 3 Days | Saad
|  | 2.2.3 | Testing the fixed errors | 1 Day | Saad
2.3 | Fixing "Apply high end features" | 2.3.1 | Existing code needs modification for the feature to be working | 3 Days | Pavana
|  | 2.3.2 | Testing and buffer | 1 Day | Pavana
2.4 | User Interface Modernization | 2.4.1 | Redesign the side pane to adopt a modern and visually appealing user interface (UI) design that aligns with current design trends. | 3 Days | Rohit
|  | 2.4.2 | Provide clear and concise descriptions for each tool or feature in the side pane, accessible through tooltips or other user-friendly means. | 4 Days | Rohit
|  | 2.4.3 | Testing and buffer | 1 Day | Rohit
2.5 | Template Design Changes/Library | 2.5.1 | Redesign existing templates to give them a fresh and updated look, aligning with current design trends | 5 Days | Rohit
|  | 2.5.2 | Expand the range of template designs to provide users with a diverse selection, catering to various styles, occasions, and artistic preferences. | 4 Days | Ayesha
|  | 2.5.3 | Testing and buffer | 2 Days | Ayesha
2.6 | Deletion Feature | 2.6.1 | Implement a "Delete" option or button within the app's user interface, allowing users to remove images from their editing workspace. | 2 Days | Ayesha
|  | 2.6.2 | When the user selects the "Delete" option, prompt them with a confirmation dialog to prevent accidental deletions. | 3 Days | Ayesha
|  | 2.6.2 | Include a keyboard shortcut (e.g., "Delete" or "Backspace" key) for users to quickly delete selected images, enhancing user convenience. | 2 Days | Ayesha
|  | 2.6.2 | Testing and buffer | 2 Days | Ayesha
2.7 | Zoom Functionality | 2.7.1 | Implement a persistent zoom control feature that remains accessible to users, even as they scroll down within the app's interface. | 2 Days | Saad
|  | 2.7.2 | Provide keyboard shortcuts (e.g., Ctrl + "+", Ctrl + "-") for zooming in and out, enhancing accessibility for users who prefer keyboard navigation. | 2 Days | Ayesha
|  | 2.7.3 | Testing and buffer | 2 Days | Ayesha
2.8 | Image Format Compatibility | 2.8.1 | Fix format conversion issues | 4 Days | Pavana
|  | 2.8.2 | Testing and buffer | 1 Day | Pavana
2.9 | Background Image Change Feature | 2.9.1 | Modify the user interface to include Background Change Selection and Background Color Selection. | 4 Days | Pavana
|  | 2.9.2 | Modify the user interface to include Image Upload, Preview Display and Download Option. | 2 Day | Pavana
|  | 2.9.3 | Testing and buffer | 1 Day | Pavana
2.1 | Resize Feature Enhancement | 2.10.1 | Modify the user interface to include a size metric in the resize feature. | 2 Days | Rohit
|  | 2.10.2 | Implement a user-selectable size metric, such as inches (in), centimeters (cm), or percentage (%), allowing users to choose their preferred unit of measurement. | 4 Days | Rohit
|  | 2.10.3 | Testing and buffer | 1 Day | Rohit
2.11 | Mosaic Feature Enhancement | 2.11.1 | Fix the Mosaic feature issues | 3 Days | Saad
|  | 2.11.2 | Testing and buffer | 1 Day | Saad
2.12 | Passport Photo Feature | 2.13.1 | Research each country requirements | 3 Days | Ayesha
|  | 2.13.2 | Modify the user interface to include this feature in the front-end along with all the necessary layouts | 5 Days | Saad
|  | 2.13.3 | Implement the back end logic for photo editing acording to respective country requirements | 5 Days | Ayesha
|  | 2.13.4 | Testing and buffer | 2 Days | Ayesha
2.13 | Image Compression Feature | 2.14.1 | Modify the user interface to include an image compression feature page and user interaction logic, such as allowing users to upload image, display the images. | 2 Days | Ayesha
|  | 2.14.2 | Implement UI elements to allow compression settings, and compression trigger and setup backend connection to frontend. | 4 Days | Rohit
|  | 2.14.3 | Research a compression algorithm that supports all types of images (.jpeg, .png etc) | 2 Days | Ayesha
|  | 2.14.4 | Implement algorithm logic over the backend and incopertae the trigger into UI | 2 Days | Ayesha
|  | 2.14.4 | Testing and buffer | 2 Days | Rohit
2.14 | Video Compression Feature | 2.15.1 | Add new Screen in Frontend for Video Compression feature | 3 Days | Rohit
|  | 2.15.2 | Implement video compression algorithm using multimeadia framework | 5 Days | Pavana
|  | 2.15.3 | Implement function to accept video from user and provide the output after compression | 2 Days | Pavana
|  | 2.15.4 | Testing and buffer | 2 Days | Pavana
2.15 | Circle Crop | 2.16.1 | Modify the user interface to include a circle crop feature | 2 Days | Saad
|  | 2.16.2 | Implement the user interaction logic, such as allowing users to select an image to crop, adjust the circle's size, position, and apply the crop effect. | 4 Days | Pavana
|  | 2.16.3 | Develop the front-end rendering component that displays the image and the circle overlay for cropping. | 5 Days | Saad
|  | 2.16.4 | Develop the back-end image processing logic that takes the user's selected circle crop parameters and applies them to the image. | 5 Days | Pavana
|  | 2.16.5 | Testing and buffer | 1 Day | Pavana
Saad
Rohit
Pavana
Ayesha

## Test Plan
2.1 | User can add or edit courses
1. Navigate to the "course management" screen from the main menu 2. Click on the plus icon in the top left of the scren 3. Enter the following information : CSE 611, Fall 2022, Alan Hunt 4. Click "Add Class" 5. The class should appear in the list of courses for fall 2022
1. Navigate to the "course management" screen from the main menu 2. Click on the course "CSE 611" 3. Change the instructor name to "John Doe" 4. Click "Save" 5. Verify that in the course listing, the instructor now says John Doe
2.1.1 | Verify that the "course listing" appears when the user clicks on "course management"
2.1.2 | Verify that on the course management screen, the plus icon appears. Clicking on the plus icon should bring up a modal dialog with fields for course name, course number, semester and instructor
2.1.3 | Verify that clicking on a course in the course listing brings up a modal dialong with the fields course name, course number, semester, and instructor Verify that all information in these fields is prefilled with the current values
2.1.4 | Verify that only valid semester values can be chosen for semesters verify that only valid instructors can be chosen for course instructors verify that duplicate courses create a warning