## Project Plan
Photo Editing
[7 empty] | February |  |  | March | [30 empty] | April | [30 empty] | May
Requirement # | Requirement | Task # | Task | Estimate | Owner | 25 | 2019-08-26 | 27 | 2018-08-28 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 31 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 13
2.1 | Passport photo creation tool backend | 2.1.1 | Creating a function for detecting a face from varies types of faces | 4 days | Arjun
|  | 2.1.2 | creating a function to detect face is striaght or not | 5 days | kalyan
|  | 2.1.3 | creating a function to detect spects | 4 days | Kalyan
|  | 2.1.4 | creating a function to change a background | 6 days | Arjun
|  |  | Create UI main page skeleton and add click functionality to feature pages | 3 days | Khyathi
|  |  | Create passport photo feature page | 3 days | Ruthika
|  |  | Integrate UI with API and cross verify the results | 2 days | Khyathi
|  | 2.1.5 | Testing and buffer | 1 day
|  | 2.1.6 | Creating Api Views | 3 days | Rakesh
|  | 2.1.7 | Creating API Contoller for Passport photo feature | 4 days | Rakesh
2.2 | Photo Resize and Crop | 2.2.1 | Creating a function for resize | 2 days | Arjun
|  | 2.2.2 | Creating a function for crop | 3 days | kalyan
|  | 2.2.3 | creating a API Controller for Phoro resize and Crop | 2 days | Rakesh
|  |  | Create Photo resize and crop feature page with default tools layout in the sidebar | 4 days | Khyathi
|  |  | Add tools and css styles for setting above | 3 days | Ruthika
|  |  | Add react crop libraries to perform crop and resize in the UI | 4 days | Ruthika
|  | 2.2.4 | Testing and buffer | 1 day
2.3 | Photo collage | 2.3.1 | Creating a fucntion to resize the photos according to the frame | 3 days | Arjun
|  | 2.3.2 | creating a function to apply filters related to the colleague | 6 days | Kalyan
|  | 2.3.3 | Creating a function to club photos based on the user requirements | 4 days | Arjun
|  | 2.3.3 | Creating a function to club photos based on the user requirements | 4 days | Kalyan
|  | 2.3.4 | Create a controller for the Photo Colleague | 3 days | Rakesh
|  |  | Create photo collage feature page | 3 days | Khyathi
|  |  | Add default collage layouts in the UI | 5 days | Ruthika
|  |  | Implement functionality to upload n number of images for collage | 2 days | Khyathi
|  | 2.3.4 | Testing and buffer | 1 days
2.4 | Noise Removal | 2.4.1 | creating a function for noise removal | 6 days | Arjun
|  | 2.4.2 | creating a function for noise removal | 6 days | Kalyan
|  | 2.4.3 | creating a API controller for Noise Removal | 3 days | Rakesh
|  |  | Create Noise removal feature page | 3 days | Ruthika
|  |  | Integrate with API and cross verify | 3 days | Khyathi
|  | 2.4.4 | Testing and buffer | 1 day
2.5 | Image Format conversion | 2.5.1 | creating a function for image format conversion | 2 days | Arjun
|  |  | Add UI functionality for image format conversion | 2 days | Khyathi
2.6 | Data Base creation and functionalities | 2.6.1 | Creating a Database | 1 day | Rakesh
|  | 2.6.2 | creating a script to update the db | 2 days | Rakesh
|  | 2.6.3 | creating a script to extract the db data | 2 days | Rakesh
|  | 2.6.4 | creating a script to delete the db data | 2 days | Rakesh
|  |  | Testing and buffer | 1 day
2.7 | Brightness and Contrast | 2.7.1 | Creating a function for brightness | 3 days | Arjun
|  | 2.7.2 | creating a function for contrast | 3 days | Kalyan
|  | 2.7.3 | creating a controller for brightness | 2 days | Rakesh
|  | 2.7.4 | creating a controller for contrast | 1 day | Rakesh
|  |  | Add feature page for brightness and contract | 4 days | Ruthika
|  |  | Add tools and css styles for setting above | 3 days | Khyathi
|  | 2.7.5 | Testing and buffer | 1 day
Arjun
Kalyan
Rakesh
Khyathi
Ruthika

## Test Plan
2.1 | User can add or edit courses
1. Navigate to the "course management" screen from the main menu 2. Click on the plus icon in the top left of the scren 3. Enter the following information : CSE 611, Fall 2022, Alan Hunt 4. Click "Add Class" 5. The class should appear in the list of courses for fall 2022
1. Navigate to the "course management" screen from the main menu 2. Click on the course "CSE 611" 3. Change the instructor name to "John Doe" 4. Click "Save" 5. Verify that in the course listing, the instructor now says John Doe
2.1.1 | Verify that the "course listing" appears when the user clicks on "course management"
2.1.2 | Verify that on the course management screen, the plus icon appears. Clicking on the plus icon should bring up a modal dialog with fields for course name, course number, semester and instructor
2.1.3 | Verify that clicking on a course in the course listing brings up a modal dialong with the fields course name, course number, semester, and instructor Verify that all information in these fields is prefilled with the current values
2.1.4 | Verify that only valid semester values can be chosen for semesters verify that only valid instructors can be chosen for course instructors verify that duplicate courses create a warning